## Ark1
| workdays | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-11-01 | 2019-11-04 | 2019-11-05 | 2019-11-06 | 2019-11-07 | 2019-11-08 | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21
Tasks
Total days
PROJECT START | Project Managment, Customer, agreement and signature
Meeting with customer |  | 1 | [38 empty] | 1
Build team | Project Manager, Content Developer, Designer, Developer, Photographer, Copywriter | 1 | [38 empty] | 1
PLANNING
Kick-off (website brainstorming) | Project Managment |  | 1 | 1 | [36 empty] | 2
Content research | Content Developer, Designer |  |  |  | 1 | 1 | 1 | 1 | 1 | [31 empty] | 5
Apply for patent "production process" | Project Manager on behalf of customer |  |  |  | 1 | [35 empty] | 1
Trademark apple juice made by Lofthus frukt og saft | Project Manager on behalf of customer |  |  |  | 1 | [35 empty] | 1
Text / copywriting | Content Developer, copywriter |  |  |  |  | 1 | 1 | [33 empty] | 2
Set copyrights for content | Content Developer, copywriter | [5 empty] | 1 | [33 empty] | 1
visit clients site, for researching production processes | Content Developer, Designer, Photographer | [7 empty] | 1 | 1 | [30 empty] | 2
visual elements, photographing | Designer, Photographer | [8 empty] | 1 | [30 empty] | 1
meeting about content, site outline and visual elements | Content Developer, Developer, Designer, Photographer | [9 empty] | 1 | 1 | [28 empty] | 2
Code solutions, coding | Developer | [11 empty] | 1 | 1 | 1 | [25 empty] | 3
Make Gantt chart | Project Manager | [14 empty] | 1 | [24 empty] | 1
Input project into Trello and add participents | Project Manager | [15 empty] | 1 | [23 empty] | 1
Project Managment meeting 1 validating planning | All | [16 empty] | 1 | [22 empty] | 1
Presentation 1 for customer | Project Managment and customer | [17 empty] | 1 | [21 empty] | 1
DESIGNING
Design sitestructure from site outline | Content Developer, Developer, Designer | [18 empty] | 1 | 1 | 1 | [18 empty] | 3
Design style Tiles | Designer | [21 empty] | 1 | 1 | [16 empty] | 2
Text content design | Content Developer, copywriter | [21 empty] | 1 | 1 | [16 empty] | 2
Photoshoot at customer site when on visit for planning | Photographer | [8 empty] | 1 | [30 empty] | 1
Project Managment meeting 2 validating design | All | [23 empty] | 1 | [15 empty] | 1
BUILD
make wireframe mobilefirst, tablets and pc | Designer | [24 empty] | 1 | 1 | 1 | 1 | [11 empty] | 4
Coding website for mobilefirst, tablet and pc | Developer | [26 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 8
copyright code and content | Content Developer, Developer | [34 empty] | 1 |  |  |  |  | 1
Testing for good user experience | Developer, tester panel | [27 empty] | 1 |  |  |  | 1 | [7 empty] | 2
Testing for good user interface | Developer, tester panel | [27 empty] | 1 |  |  |  | 1 | [7 empty] | 2
Browser platform testing | Developer | [32 empty] | 1 | 1 | [5 empty] | 2
Project Managment meeting 3 validating build | All | [34 empty] | 1 |  |  |  |  | 1
Final adjustments | Content Developer, Developer, Designer | [35 empty] | 1 | 1 |  |  | 2
Project Managment meeting 4 validating setup | All | [37 empty] | 1 |  | 1
Launch day! | Project Manager, Content Developer, Designer, Developer | [38 empty] | 1 | 1
59